## HUIT FY14 Top 10 Goal Status
HUIT FY14 Top 10 Priorities
|  | Status Update as of: | 2013-11-20
Goal | Owner | Milestones | Complete by: | Status
Roll out a customer engagement (CE) process focused on listening to customer needs (SG1) | SW*, SEO | Communicate CE program schedule to HUIT relationship managers, SLT, and CIOs | 2013-10-30
|  | Train HUIT relationship managers on program implementation | 2013-10-31
|  | Complete initial round of engagement meetings with Schools and CA | 2013-12-20
Create and meet targets for migration of email users to O365 (SG8) | SW*, SEO | Achieve "Production Ready" status for O365 | 11/13/2013 (rev 12/17/13)
|  | Complete early adopter phase of O365 conversions for up to 1,000 users | 2014-01-14
|  | Migrate 30% of mailboxes to O365 - estimated 4K to 6K mailboxes | 2014-06-14
Create a simplified, user-focused service catalog (SG17) | SEO | Re-design the HUIT site to have a clearer home page, navigation, and more accessible Service Catalog pages | 2014-02-01
|  | Categorize all services in SNow by audience: end user, customer, IT provider | 2014-04-01
|  | Implement search-by-user-type and supporting communication materials for fall start-up roll | 2014-07-30
Develop HUIT strategy for business continuity and disaster recovery (SG 25) | TFA*, CH | Develop and document an architectural approach for high availability and disaster recovery for green field applications. | 2014-06-30
|  | Develop and document an architectural approach for moving existing applications to a next generation disaster recovery solution. | 2014-06-30
|  | Facilitiate a tabletop business continuity planning exercise for the HUIT SLT. | 2014-06-30
Develop and begin to implement a comprehensive enterprise architecture for HUIT (SG26) |  | Establish and implement an architectural review as part of the review model for ITCRB funded projects | 2014-02-28
|  | Develop an integration plan for software and operations management | 2014-06-30
|  | Draft and review a technology road map | 2014-06-30
Advance CIO Council Strategic Initiatives - SG27
IAM - SG 27A | J. Snyder | Develop an IAM Strategic Plan outlining key milestones and activities to achieve the program objectives | 2014-01-31
|  | Deliver Sailpoint solution to provide direct provisioning of identities into Active Directory | 2014-06-30
|  | Provide a formal Harvard-based IdP to become an active participant in the InCommon Federation | 2014-03-31
HarvardX - SG 27B | SSE | Complete pivot of organization from ad-hoc to structured (HR, process, IT) | 2014-03-01
|  | Develop and fully implemented tierd support and financial models for startup, version 2 and multi-modal courses & modules (those that are offered simultaneously across Hx, school and/or DCE) | 2014-03-01
Meet milestones established in 8 point plan
LME - SG 27C | SSE | Converge Black Pearl & LME 1.0 teams/processes into LME 2.0 team and unified project plan | 11/30/13*
|  | Deliver FY2014 version of LME production services | 2014-06-13
|  | Seek and obtain implementation project funding | 2014-03-15
Collaboration - SG 27D | SW*, BW | Define shared collaboration vision | 2013-12-01
|  | Deliver summary of current state and identify gaps in light of future vision | 2014-02-01
|  | Provide options with recommendation of how to close the gaps | 2015-02-15
Video - SG 27E | SSE | Reboot and deliver lecture capture service | 3/15/14*
|  | Deliver FY2014 version of production services | 2014-06-15
|  | Develop and confirm sustainable financial model for shared services | 2014-03-15
Research Computing - SG 27F | JW*, JC | Complete full installation of NephoEngineering platform on Physical RC Infrastruture with shared RC Object Store | 2013-12-20
|  | Implement 5 use cases of NephoEngineering platform for developers from Academic Technology and Research Computing platforms | 2014-03-28
|  | Conduct elastic computing using Nepho platform from Holyoke to IaaS provider for HPC, e.g. AWS/RackSpace/GCE | 2014-06-30
SIS - SG 27G | J. Shaffner | Finalize detailed project schedule and resource plan for Wave 0 (Student Financials) and Wave 1 (College, GSAS + PhD Programs in Schools, SEAS, HDS) | 2013-12-31
|  | Complete design of PS Campus Solutions and Student Analytics including interfaces, customizations, conversion for Wave 0 (Student Financials) | 2014-03-31
|  | Obtain commitments from Wave 2 schools to join the common platform or build bridges for seamless interoperation between HU SIS and local systems. | 2014-06-30
Information Security - SG 27H | CH | Complete plan for Communications/Awareness Program | 2013-11-30
|  | Complete annual School self-assessment and compliance process | 2014-02-01
|  | Launch new Information Security policy | 2014-03-28
Implement a computing-on-demand pilot for FAS research computing and HUIT developers that uses the same technology for both purposes - SG 28 | JW*, JC | Complete full installation of NephoEngineering platform on Physical RC Infrastruture with shared RC Object Store | 2013-12-20
|  | Implement 5 use cases of NephoEngineering platform for developers from Academic Technology and Research Computing platforms | 2014-03-28
|  | Perform elastic computing using Nepho platform from Holyoke to IaaS provider for HPC, e.g. AWS/RackSpace/GCE | 2014-06-30
Define and implement project portfolio reporting - SG 34 | TFA | Implement project reporting database to support online portfolio reporting for ATS, INF, SPT, S&P with 90% of projects previously reported on spreadsheets reported through database (Ex ITCRB) | 2013-11-30
|  | Implement Portfolio reporting for ITCRB funded projects with all ITCRB project reports produced from the reporting database. | 2014-01-31
|  | Implement multi-dimensional portfolio reporting, leveraging meta-data (e.g. investment type, customer area, strategic initiative, etc.) | 2014-02-28
Define and identify key positions (KPs); create cross-training, retention, and succession plans for each (SG 38) | KI | Identify KPs and work with managers to identify and vet with SLT | 2013-12-01
|  | Complete data gathering on KPs based on "stay" interviews conducted by mgrs with staff in those KPs and HR review of exit interview data and upward feedback reports | 2014-02-28
|  | Finalize retention, succession, and cross-training plans for KPs | 6/30/2014 + ongoing
Implement a comprehensive HUIT communication strategy for internal and external audiences, including a strategic organization of HUIT’s web presence - SG 40 | KD | A HUIT Communication Steering Committee will govern the development of a new HUIT website and a new common layout and taxonomy for HUIT child sites
Create a new emailed HUIT periodical.

## Team Communication
<Project Name>
Project Team Communication Plan
| Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Reports | Project status report | Regular update on critical project issues | E-mail | Weekly | Project Manager | Project Manager Project Sponsor Project Team
| Quality audit report | Regular update on project quality performance | E-mail | Weekly | Quality Manager | Project Manager Project Sponsor Project Team Quality Manager
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
Presentations | Project review | Project status update | Meeting | Monthly | Project Manager | Project Manager Project Sponsor Project Team
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
Project Announcements | Task reminders | Task owner schedule reminders | E-mail | Daily | Project Coordinator | Project Manager Project Team
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
Reviews and Meetings | Team meeting | Meeting to review project status | Meeting | Weekly | Project Coordinator | Project Manager Project Sponsor Project Team Quality Manager
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
Team Morale | Team event | Regularly schedule team morale events | Event | Quarterly | Project Sponsor | Project Manager Project Sponsor Project Team
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>
| <Deliverable> | <Description> | <Delivery Method> | <Frequency> | <Owner> | <Audience>